## Slide 1: Micromouse
Shashank
Shresht
Panshul
Snigdha
Vaishnav
Prahelika
Abishek
Pranav

## Slide 2: Workflow Overview
Hardware:
    Efficient Power Supply
    Microcontroller Design
    Sensor Integration
    Motor Drive & Locomotion
Algorithm:
    Wall-Follower
    Floodfill
Software:
    ARM Code Development
    Algorithm Implementation

## Slide 3: Hardware
Power Supply Design:
    Mouse requires 5V and 3.3V supplies for various subsystems and booster for fan
    Responsible Team: Shashank and Pranav
    Work Done: 5V and 3.3V LDO’s working
    5V switching regulator working
    Pending: 3.3V fabrication to be done
    Boost converter design
    Progress: 80%

## Slide 4: Hardware
Microcontroller Design:
    Identify a high performance microcontroller for the mouse and integrate it
    Responsible Team: Pranav
    Work Done: Designs for ATmega328p and STM32F405 ready
    Pending: Fabrication and Testing
    Progress: 25%

## Slide 5: Hardware
Sensors:
    Design a reliable IR Emitter-Receiver Sensing System with Gyroscope and Encoder for feedback
    Responsible Team: IR Emitter-Receiver – Vaishnav
    Gyroscope – Shresht
    Encoder – Shashank
    Work Done: Gyro and Encoder Tested
    Pending: IR Emitter-Receiver Placement
    Custom Gyro and Encoder design and integration
    Progress: 10%

## Slide 6: Hardware
Motor Drives:
      Design a efficient motor driver for the mouse
      Responsible Team: Prahelika and Pranav
      Work Done: One of the 3 choices has been tested
      Pending: Design and Fabrication of the other choices
      Progress: 33%

## Slide 7: Algorithm
Wall Follower:
      Implement an algorithm that prefers a specific turn always
      Responsible Team: Panshul, Vaishnav and Pranav
      Work Done: Right hand follow code has been written
      Pending: Test and expand it for more no. of sensors
      Progress: 5%

## Slide 8: Algorithm
Flood-fill:
    Build an algorithm that finds the shortest path of a maze
    Responsible Team: Pranav
    Progress: 0%

## Slide 9: Software
ARM Code Development:
      Make a basic template for the required controller
      Progress: 0%
Algorithm Implementation:
      Progress: 0%